## Example 1
Activity ID | Description | Start | Finish | R00 OD | R10 OD | Variance
EX1-1000 | Site mobilization | 2027-01-04 | 2027-01-18 | 10 | 14 | 4
EX1-1010 | Temporary fencing install | 2027-01-05 | 2027-01-20 | 12 | 16 | 4
EX1-1020 | Utility survey | 2027-01-08 | 2027-01-22 | 10 | 10 | 0
EX1-1030 | Topsoil stripping | 2027-01-15 | 2027-02-05 | 15 | 21 | 6
EX1-1040 | Bulk earthworks | 2027-02-01 | 2027-03-15 | 30 | 42 | 12
EX1-1050 | Foundation piling | 2027-03-01 | 2027-04-20 | 40 | 50 | 10
EX1-1060 | Pile caps concrete | 2027-04-10 | 2027-05-05 | 18 | 24 | 6
EX1-1070 | Ground beams | 2027-04-25 | 2027-05-18 | 16 | 22 | 6
EX1-1080 | Backfill and compaction | 2027-05-10 | 2027-05-25 | 10 | 15 | 5
EX1-1090 | Site drainage phase 1 | 2027-05-15 | 2027-06-10 | 20 | 25 | 5

## Example 2
Activity ID | Description | Start | Finish | R00 OD | R10 OD | Variance
EX2-2000 | Design freeze package A | 2027-02-01 | 2027-02-15 | 10 | 8 | -2
EX2-2010 | Long-lead switchgear order | 2027-02-05 | 2027-08-30 | 150 | 175 | 25
EX2-2020 | Structural steel fabrication | 2027-03-10 | 2027-06-20 | 70 | 84 | 14
EX2-2030 | Steel erection zone A | 2027-06-25 | 2027-08-10 | 35 | 45 | 10
EX2-2040 | Steel erection zone B | 2027-07-15 | 2027-09-05 | 38 | 50 | 12
EX2-2050 | Roof deck install | 2027-09-01 | 2027-09-25 | 18 | 22 | 4
EX2-2060 | Building envelope | 2027-09-15 | 2027-11-30 | 55 | 70 | 15
EX2-2070 | MEP rough-in level 1 | 2027-10-01 | 2027-12-10 | 50 | 60 | 10
EX2-2080 | MEP rough-in level 2 | 2027-10-15 | 2027-12-22 | 48 | 58 | 10
EX2-2090 | Commissioning readiness review | 2027-12-05 | 2027-12-20 | 10 | 12 | 2

## Instructions
OD Comparison — Template Instructions
Use this workbook as a starting point for building an Original Duration (OD) comparison.
File format
• One tab per comparison. The tab name is used as the chart title.
• The first row of each tab MUST be a header row.
• Columns, in this exact order:
A Activity ID
B Description
C Start
D Finish
E <start version> OD (e.g. R00 OD) — numeric days
F <end version> OD (e.g. R10 OD) — numeric days
G Variance — numeric (end − start); if blank it is computed
Rules
• Columns E and F must contain numbers (days). Rows without valid numbers are skipped.
• Use one row per activity. Duplicate Activity IDs are allowed but discouraged.
• The 'Instructions' tab (this tab) is IGNORED by the app — keep it here for reference.
• Save the file as .xlsx before uploading.
Support
For any questions, contact pmelloconsult@systech-int.com (Peter Mello).